## Example Of Matrix (3 Levels)
Level 1 - All Company Projects
Principle Responsibility |  | CEO | Affected Director | Affected Line Manager | Implementer | Project Manager | Affected Staff Member | Elected Representative
1 | Principle responsibility chart | D | C | C |  | X/P | I | C
2 | Milestone plan & project responsibility chart | I | D | X | X | X/P | X | I
3 | Allocation of resources (global level) | D | d | X | C | P | I | I
4 | Milestone report |  | D | C | C | X/P | I | I
5 | Activity planning binding completion date |  | C | C | C | X/P
6 | – select implementer |  |  | d | C | X/P
7 | – determine duration of activity |  |  |  |  | X/P | X
8 | – determine start time & sequence |  |  |  |  | D
9 | – commit line resources |  |  | d | d
10 | – release line resources |  |  | X/P | X
11 | – execute activity |  |  |  | X | P | C
12 | Activity responsibility |  |  |  | C | X/P
13 | Activity report |  |  |  | X | P
14 | Work environment matters |  | D | C |  | P | C | C
Level 2 - Major Phases On One Project - Example: Head Office IT Systems
Project Responsibility |  | Senior Management Team (SMT) | Chief Executive Officer (CEO) | Project Board (PB) | Functional & Regional Reps | Project Sponsor | Company Project Managers | IT Advisors | Interviewees | Users | Measurement Team | Evaluation Team | Negotiation Team | Implementation Team | Package Vendors | Hardware Vendors
1 | Project Process Revision | I | D | C |  | X |  | A
2 | Requirements Definition Document | D | C | P | C | d |  | X | C
3 | Supplier & System Selection | D | C | P |  | d |  | X |  | I |  | X |  |  | C | A
4 | Current System Assessment | D | C | P | C | d |  | X |  |  | X
5 | Business Case & Capital Application | D | C | X | C | d |  | A |  |  | C | C | C |  | C | C
6 | Conference Room Pilot |  |  | D | C | d |  | A |  | C |  | C | C |  | d | d
7 | Ledger Implementation | D | d | I | C | d | P | A |  | I |  |  |  |  | d | d
8 | Payroll Implementation | D | d | I | C | d | P | A |  | I |  |  |  |  | d | d
9
10
11
12
13
14
Level 3 - Repeating Activities On One Project - Example: Head Office IT Systems (Also See 'Assignments' On Project Schedule)
Activity Responsibility |  |  |  | Project Manager |  | Project Sponsor |  | Chief Executive Officer |  | User Representative |  | IT Consultant
1 | Weekly CEO review & update |  |  |  |  | X |  | C/T
2 | SMT review at 'General' Board Meetings |  |  |  |  | X |  | C
3 | SMT review at 'Financial' Board Meetings |  |  |  |  | X |  | C
4 | Feedback developments & reports to PCB |  |  | I |  | X |  |  |  | I |  | I
5 | Monitor project budget |  |  | I |  | X |  | I |  | I |  | C
6 | Monitor project schedule |  |  | I |  | I |  | I |  | X |  | C
7 | Assimilate history of company & the client base |  |  |  |  | X |  | T
8 | Relate project to 5-Year Plan |  |  |  |  | X |  | T |  |  |  | A
9 | Identify 2 'dry run' candidates each presentation |  |  | X |  | C |  | I |  | I |  | I
10 | Challenge 'technology evangelism' (be sceptical) |  |  | X |  | I |  |  |  | I |  | I
11 | Liaise with IT suppliers |  |  |  |  | I | [5 empty] | X/P
12
13
14
15
16
X - Executes the work
D - Takes decision solely
d - Takes decision jointly
P - Manages progress
T - Transfer of Information/Knowledge
C - Must be consulted
I - Must be informed
A - Available to advise
S - Provides necessary support
X – Executes the work
D – Takes decision solely/ultimately
d – Takes decision jointly
P – Manages progress
T – Transfer of information/knowledge
C – Must be consulted
I – Must be informed eg copy documents
A – Available to advise
S – Provides support eg techniques or documentation
X – Executes the work
D – Takes decision solely/ultimately
d – Takes decision jointly
P – Manages progress
T – Transfer of information/knowledge
C – Must be consulted
I – Must be informed eg copy documents
A – Available to advise
S – Provides support eg techniques or documentation
X – Executes the work
D – Takes decision solely/ultimately
d – Takes decision jointly
P – Manages progress
T – Transfer of information/knowledge
C – Must be consulted
I – Must be informed eg copy documents
A – Available to advise
S – Provides support eg techniques or documentation

## Group Members (List Form)
Group | Representative Type | Name
SMT | Main | CEO
| Main | All Directors
| Main | All Associate Directors
| Main | All Controllers
CEO | Main | XXX
| Reserve | XXX
PCB | Client Sponsor | XXX
| Client | XXX
| Client | XXX
| IT Adviser | Martin Tate
Functional & Regional Reps | BDM Main | XXX
| BDM Reserve | XXX
| Governance | XXX
| Customer Service Main | XXX
| Customer Service Reserve | XXX
| Engineering Main | XXX
| Engineering Reserve | XXX
| IT Main | XXX
| IT Reserve | XXX
| Payroll & Personnel Main | XXX
| Payroll & Personnel Reserve | XXX
| Purchasing Main | XXX
| Purchasing Reserve | XXX
| Ops Retail Main | XXX
| Ops Retail Reserve | XXX
| Ops Other Retail Main | XXX
| Ops Other Retail Reserve | XXX
| Other Function A Main | XXX
| Other Function B Reserve | XXX
| Other Function B Main | XXX
| Other Function B Reserve | XXX
| Other Function C Main | XXX
| Other Function C Reserve | XXX
Project Sponsor | Main | XXX
| Reserve | XXX
Client Project Managers | Module A | XXX
| Module B | XXX
IT Advisors | Current | Martin Tate
| Backup Source 1 | XXX
| Backup Source 2 | XXX
Interviewees | Note | See Requirements Document Appendix: Interview Programme
Users | Note | Relevant set TBD each time info is disseminated
Measurement Team | System A | XXX
| System B | XXX
| System C | XXX
| System D | XXX
| System E | XXX
| System F | XXX
| System G | XXX
Evaluation Team | Functional Rep A | XXX
| Functional Rep B | XXX
| Functional Rep C | XXX
| Functional Rep D | XXX
| Functional Rep E | XXX
Negotiation Team | Director | XXX
| IT | XXX
| Purchasing | XXX
Implementation Team | Module A | XXX
| Module B | XXX
| Module C | XXX
| Module D | XXX
| Module E | XXX
| Module F | XXX
Package Vendors | Preferred Candidate | XXX
| Reserve Candidate | XXX
Hardware Vendors | Supplier | XXX