## RRM-SolutionSelectIon
Proj Responsibility |  | Senior Mngmnt Team (SMT) | Project Board (PB) | Project Sponsor | Project Manager | Evaluation Team | Interviewees | Negotiation Team | Implementation Team | Software Suppliers | Hardware Suppliers | IT Procurement Advisors | Change Mngmnt Advisors
1 | Authorise project | D | C | C | P | [6 empty] | T | T
2 | Determine scope | I | D | C | P | I |  | I |  | I | I | S | S
3 | Study feasibility inc cost | I | C | d | d | C |  | I |  | C | A | S | S
4 | Establish phasing | I | D | C | P | I | I | I |  | I | A | S | S
5 | Research best practice (desk search) |  | I | I | P | I |  |  | I | A |  | X | T
6 | Capture requirements (interviews) |  | I | C | P |  | C |  |  |  | A | X | C
7 | Document requirements (RDD/SoUR) |  | I | C | P | I | C |  | I |  | I | X | I
8 | Weight requirements |  | X | C | P |  | I |  | I |  | I | S | I
9 | Trawl marketplace |  |  | I | P |  |  |  |  | C |  | X
10 | Evaluate longlist (RFI) |  |  | I | D | X |  |  |  | C |  | S
11 | Review longlisting and shortlist |  | X | C | A |  |  |  |  | I | I | S
12 | Detailed eval of shortlist (RDD/SoUR) |  |  | I | P | X |  |  |  | C |  | S
13 | Score for fit |  |  | I | P | X |  |  |  | C |  | S | I
14 | Analyse gaps |  |  | I | P | X |  | I | I | A |  | S | A
15 | Review eval and select demos |  | X | C | A |  |  |  |  | I | I | S | C
16 | Demonstrate preferred candidates | C | C | C | P | C,T | C | I | I | X | I | S | C
17 | Check reference sites |  | I | I | X | C |  | I | I | C | I | S | A
18 | Negotiate terms | C: I; C: I; P: P; I: X; X: C; S: S
19 | Agree contract | d | d | C | P |  |  | C |  | C |  | S | I
20 | Install system | D |  |  | P | C | I |  | X | C | S | A | A
X - Executes the work
D - Takes decision solely
d - Takes decision jointly
P - Manages progress
T - Transfer of Information/Knowledge
C - Must be consulted
I - Must be informed
A - Available to advise
S - Provides necessary support
X – Executes the work
d – Takes decision jointly
D – Takes decision solely/ultimately
P – Manages progress
T – Transfer of information/knowledge
C – Must be consulted
I – Must be informed eg copy documents
A – Available to advise
S – Provides support eg technique/documentation