## Checklist
WBS | Tasklist - Off-The-Shelf IT Solutions: A practitioner's guide to selection and procurement
1 | Project scoping (Chapter 3)
1.1 | Prepare resources
1.1.1 | Distribute sizing spreadsheet for completion
1.1.2 | Capture metrics for business case calculations - such as value of saved hours
1.1.3 | Get organisational background documentation from website, operations manuals, published plans or internal strategy documents
1.1.4 | Research sources of likely requirements such as meeting minutes
1.2 | Compile scoping input list
1.2.1 | Research scoping list sources
1.2.2 | Extract entries from research & existing material
1.2.3 | External proof & review
1.3 | Scoping workshop
1.3.1 | Agree presentation with Project Sponsor (& Workshop Chair if different)
1.3.2 | Write glossary if needed
1.3.3 | Create scoping input lists - numbered & titled
1.3.4 | Triage entries in meeting
1.3.5 | Distribute output lists for confirmation
2 | Requirements definition interviews (Chapter 4)
2.1 | Confirm interviewees list, with groupings to workshop
2.2 | Email introduction from project sponsor
2.3 | Make requirements definition interview appointments, or organise assistant to do so
2.4 | Create prompts as topic notes or matrix of questions
2.5 | Organise 'props' for meeting room, such as sample products
2.6 | Create & send pre-interview briefing sheet
2.7 | Generate note-taking formats
2.8 | Conduct semi-structured interview programme
2.9 | Adjust interviewee list as necessary - confirm with PM or Sponsor
2.10 | Collect background for appendices such as current system
3 | Requirement documentation (Chapter 5)
3.1 | Ensure collected samples are marked to tie to interview session
3.2 | Organise notes into requirements catalogue
3.3 | Get business volumes (collection maybe delegated)
3.4 | Create requirement categories - agree with sponsor
3.5 | Mark category onto all requirements
3.6 | Write or dictate new requirements
3.7 | Incorporate standard requirements
3.8 | Process any written submissions of requirements
3.9 | Transfer selected requirements from scoping workshop output
3.10 | Transfer from business volumes document
3.11 | Back-check to collected samples & sweep notes especially volumes
3.12 | Attach current system samples as appendix
3.13 | Create or update glossary if necessary
3.14 | Standard appendices
3.14.1 | Interviewee list
3.14.2 | Paste interviewee-supplied samples from current systems, or scan paper samples
3.14.3 | Glossary of terms (as appendix or separate document if shared across projects)
3.14.4 | Pre-interview background document
3.15 | Release for comment by sponsor, PM, all interviewees (depending on version)
3.16 | Requirements revisions after comments
3.16.1 | New requirements
3.16.2 | Changes to existing requirements
3.16.3 | Retitle requirements to match reworded content
3.16.4 | Moves to Project Notes appendix if not requirement
3.16.5 | Proof
3.16.6 | Update revisions history section
3.16.7 | Release notes - last appendix of Project Notes will be suppressed from supplier copies
4 | Weights for importance (Chapter 5)
4.1 | Voting spreadsheet
4.1.1 | Compile voting spreadsheet including voter name, coloured columns, transfer requirement titles, fill category
4.1.2 | Mark rotating lead voters with dashes - every 10 or divide number of scored requirements by number of voters
4.1.3 | Create agreed weight distribution chart
4.2 | Other preparation for weighting meeting
4.2.1 | Confirm weighting team
4.2.2 | Create name cards for weighting team members
4.2.3 | Standard meeting tasks including date, venue & notify attendees
4.2.4 | Print standard document to define weights
4.2.5 | Print sample page of voting spreadsheet
4.2.6 | Compile meeting progress spreadsheet
4.2.7 | Example of weighted attribute scoring mechanism - article on BCS extras page
4.2.8 | Print spares of prime section of requirements & own copy for revision annotations
4.2.9 | Create presentation or check standard is suitable
4.3 | Meeting brief
4.3.1 | Introductions (if new members)
4.3.2 | introduce next project stages especially scoring mechanism
4.3.3 | Definitions for weights
4.3.4 | Explain outcomes needed from weighting meeting
4.4 | Requirements revisions after weighting meeting
4.4.1 | Splits, deletes & modifications - from markups
4.4.2 | Moves to Project Notes appendix
4.4.3 | Reword & retitle
4.4.4 | New Requirements
4.4.5 | Update Revisions History section
4.4.6 | Align voting spreadsheet with new requirement numbers & titles
4.4.7 | Proof then modifications
4.4.8 | Release notes - last appendix suppressed
5 | Longlist (Chapter 6)
5.1 | Longlist sources to trawl marketplace
5.1.1 | Trawl online technology articles
5.1.2 | Trawl online product databases - niche
5.1.3 | Check verical magazines eg Manufacturing Management
5.1.4 | Ask suppliers, customers, possibly competitors
5.1.5 | Contact Computer Users Information Service CUIS
5.2 | Creating longlist
5.2.1 | Load from previous projects
5.2.2 | Load any suppliers already contacted on project so far
5.2.3 | Prepare telephone call notes - project information, ask if interested, dates RFI out/in, who best contact
5.2.4 | Ring new potential candidates
5.2.5 | Load new suppliers from latest trawl of marketplace
6 | Request for Information - RFI (Chapter 7)
6.1 | RFI creation
6.1.1 | Check if tendering regulations apply for this project (eg OJEU, GSA)
6.1.2 | Ensure have up-to-date, weighted requirements
6.1.3 | Rules for inclusion: high weight or 'litmus test'; discriminates; can test by documented closed question; not concommitant; not seatbelt; spread of sections
6.1.4 | Extract RFI criteria from requirements
6.1.5 | Create RFI - all items numbered, in separate rows
6.1.6 | Write project background for candidates (extract from requirements document)
6.1.7 | Consider attaching or extracting glossary
6.2 | Finalising RFI
6.2.1 | Include terms or include project glossary
6.2.2 | Complete background - company, project, method, response, timing
6.2.3 | Complete 'answers' - assessment criteria
6.2.4 | Circulate to Sponsor or PB for approval
6.2.5 | Ensure supplier version has answers removed
6.3 | Distribute RFI to longlist
6.3.1 | Prepare covering email
6.3.2 | Distribute RFI email with attachment - BCC to list or individual e-mails - candidates should not see each other
6.3.3 | Clarify if enquiries - broadcast general answers to all candidates as appropriate
7 | Mark RFI responses (Chapter 7)
7.1 | Receiving responses to RFI
7.1.1 | Collate replies
7.1.2 | Check copied to Project Inbox - forward if not
7.1.3 | Acknowledge safe receipt
7.1.4 | Mark status on longlist matrix
7.1.5 | Save attachments including response & appendices to folder per candidate
7.1.6 | Save covering email as document in same folder
7.1.7 | Check supplier/product name is in each document name - rename if necessary
7.1.8 | Print each candidate's main RFI with attachments
7.1.9 | Print all notifications of withdrawals ('turndowns') as evidence for meeting
7.2 | Prepare marking spreadsheet
7.2.1 | Ensure have columns with criteria (transfer from RFI) plus candidates across page
7.2.2 | Setup headings to mark categories
7.2.3 | Filter to suppress headings for assessment meeting
7.2.4 | Setup format of price-performance Bubble Chart - X = Cost, Y = Points, Bubble = PPI
7.3 | RFI assessment meeting (marking)
7.3.1 | Setup working room for RFI marking (need space to spread out, and screen visible)
7.3.2 | Assess to marking scheme - one RFI question for all candidates, then next question
7.3.3 | Agree shortlist with Project Board
7.3.4 | Contact suppliers with through/park outcome
7.3.5 | Send non-disclosure agreement to shortlisted suppliers
7.3.6 | Send requirements document (less internal appendices) & project background document
8 | Evaluation 'tour' arrangements (Chapter 8)
8.1 | Agree dates with shortlisted suppliers - get directions
8.2 | Organise itinerary, hotels, transport, tickets
8.3 | Notify evaluation team of arrangements
8.4 | Brief evaluation team
8.5 | Create control spreadsheet for meeting sequence & schedule to reflect availability of evaluation & response team
8.6 | Print requirements documentation as notes format (reduce to 70%, each meeting with watermark for candidate name)
9 | Evaluation meetings - open/close for suppliers (Chapter 8)
9.1 | Opening meeting (before 1st main evaluation session/category)
9.1.1 | Introductions
9.1.2 | Verify time constraints on attendees
9.1.3 | Highlight objective of sessions
9.1.4 | Introduce next stages (briefly, to give meeting context)
9.1.5 | Stress need for pace
9.1.6 | Stress benefit of brief introductions - save time for main sessions
9.1.7 | Explain general demonstration OK - if gives shorthand for later responses
9.1.8 | Verify Appendix 1 Conditions OK
9.2 | Evaluation meetings with suppliers
9.2.1 | Collect samples - tag to requirement number
9.2.2 | Conduct end-of-day reviews with evaluation team
9.3 | Closing meeting (after last evaluation session)
9.3.1 | Advise scoring meeting dates - confirm supplier contact for period if evaluation team have queries
9.3.2 | Advise date outcome will be available
10 | Scores for fit on weighted attribute matrix (Chapter 9)
10.1 | Scoring formats (inputs to meeting)
10.1.1 | Create empty WAM spreadsheet including column headings
10.1.2 | Load requirements titles (from voting spreadsheet or requirements document direct)
10.1.3 | Add columns if needed for more candidates and enter candidate names across scores columns
10.1.4 | Set all candidate scores to 0.1
10.1.5 | Fill down category keywords
10.1.6 | Insert subtotals at change of Category to Requirement Number, Weight, Maximum & all Fit Xtd columns)
10.1.7 | Adjust formulae at total & subtotal lines for Count & Average
10.1.8 | Transfer weights from weighting meeting as necessary
10.1.9 | Add %age Fit to one Subtotal entry and copy to others
10.1.10 | Protect sheet, test can only input to Title & Match columns
10.1.11 | Print sample page of (unfinished) scoring spreadsheet for meeting
10.1.12 | Generate definitions document format by merging standard framework with requirement number/titles
10.1.13 | Create definitions front & version control sheet
10.1.14 | Add 'purpose of definitions' sheet if necessary
10.1.15 | Print sample definitions page for scoring meeting
10.1.16 | Create schedule and progress control spreadsheet from requirement ranges
10.2 | Run scoring meeting
10.2.1 | Brief scoring team in scoring spreadsheet & definitions
10.2.2 | Handout scoring process reference sheet
10.2.3 | Show sample page of scoring spreadsheet - explain weights transferred from voting
10.2.4 | Show sample definitions
10.2.5 | Explain scoring will be blind - weight should not influence process of agreeing score for fit
10.2.6 | Advise team to lay out their notes in a way that aids reliable product recognition amongst the group
10.2.7 | Give summary statistics especially number of scored requirements
10.2.8 | Score for fit in range 0-3 - remember need specific definitions of scores for each requirement (will be attached to contract)
10.2.9 | For each requirement, identify variations in the packages â€“ the spread of capability
10.2.10 | Discard â€˜golden featuresâ€™ - over-capacity or over-provision where solution does more than required, and surplus is not beneficial
10.2.11 | Record basis for allocating points, only define the scores you allocate, rather than all four (not a ranking, some candidates will score the same)
10.2.12 | Record the capability needed for each score in scoring definitions (one definition per requirement per score used)
10.2.13 | Record the scores for each candidate on the scoring spreadsheet
10.3 | Verifying scores with candidates
10.3.1 | Copy scoring spreadsheet to generic supplier version
10.3.2 | Unhide all columns & rows
10.3.3 | Add in general/common version new columns for supplier applications (difference in current score versus application, supplier comment)
10.3.4 | Delete columns such as source (if used), weight & extended scores
10.3.5 | Delete surplus sheets
10.3.6 | Create 'cut down' versions - one per supplier showing only their scores, not competitor
10.3.7 | E-mail to confirm scores with IT suppliers - send definitions & cut-down matrix for their scores - remind requirements document not changed
10.3.8 | When returned, review supplier bids for more or less points - adjust scores - adjust definitions if necessary
10.4 | Analysis of scoring spreadsheet
10.4.1 | Review fit established (so far)
10.4.2 | Form initial opinion on whether should go ahead
10.4.3 | Find mandatory not yet scored, due to lack of information (5 & 0.1)
10.4.4 | Find others not yet scored, due to lack of information (All & 0.1)
10.4.5 | Find any mandatory requirements with score of 0. ('Fatal flaws' or apply to drop weight 5 to 4)
10.4.6 | Find mandatory requirements with score of 1
10.4.7 | Revise opinion on whether should go ahead (stop/go recommendation)
10.4.8 | Analyse scores for trends or highlights for meeting
10.4.9 | Create chart of fit
11 | Selecting demonstration candidates (Chapter 9)
11.1 | Preparation
11.1.1 | Standard meeting tasks including date, venue & notify attendees
11.1.2 | Confirm recommendations with evaluation team
11.1.3 | Assemble briefing notes & handouts - recommendations & decisions needed
11.1.4 | Distribute handouts before meeting if beneficial
12 | Demonstrations (Chapter 10)
12.1 | Specification
12.1.1 | Filter requirements document scores to high weight and high score (usually 3+, 2+)
12.1.2 | Select requirement section and title/number combination
12.1.3 | Transfer list & build table around it - add demonstration step numbering
12.1.4 | Distribute for comment
12.2 | Demonstration data
12.2.1 | Research & collate demonstration data
12.2.2 | Check data to outline for gaps
12.2.3 | Send outline and data to demonstration suppliers
13 | Reference sites (Chapter 11)
13.1 | Request reference sites with contact details & appointments
13.2 | Create questions list
13.3 | Send ahead to referees
13.4 | Send courtesy copy to suppliers
13.5 | Conduct interviews - update questions table with notes
13.6 | Play back notes to referee
14 | Selecting preferred for negotiation (Chapter 12)
14.1 | Preparation
14.1.1 | Standard meeting tasks including date, venue & notify attendees
14.1.2 | Create presentation with summary of progress
14.1.3 | Create or update and review chart of fit
14.1.4 | Distribute handouts before meeting if beneficial
14.2 | Final selection discussion - review scores, demonstrations, reference sites
14.2.1 | Discuss overall match between the candidates and business requirements
14.2.2 | Discuss technical fit of each product
14.2.3 | Discuss fit of the supplier services
14.2.4 | Discuss investment likely to be required
14.2.5 | Discuss ability of suppliers to meet the implementation schedule
14.2.6 | Discuss calibre of supplier resources and strategic alliances
14.2.7 | Discuss chemistry between your organisation and the supplier
14.2.8 | Agree number of negotiation candidates
15 | Negotiation and agreement (Chapter 12)
15.1 | Analyse scores for important shortfalls to negotiate (high weight, low score)
15.2 | Compile/agree negotiation sheet including Best, Worst & Open
15.3 | Distribute negotiation agenda to internal negotiation team for information and agreement
15.4 | Conduct negotiations
15.5 | Document agreements in Agreed column
15.6 | Follow up outstanding points
15.7 | Compile contract from supplier and customer content, especially attaching requirements, scores, definitions
16 | Possible contract components and attachments (Supplement to Chapter 12)
16.1 | Attachments provided by customer
16.1.1 | Baselined requirements document (as statement of requirement)
16.1.2 | Scores for this candidate (as agreed statement of fit)
16.1.3 | Scoring definitions (as statement of customer expectations)
16.2 | Some likely standard contract components provided by supplier
16.2.1 | Statement of work (implementation, integration, pilot, services)
16.2.2 | Training (for product, supplemental)
16.2.3 | Delivery and license (delivery, data conversion, grant and limitations for license, source code Escrow)
16.2.4 | Limitation of liability (limitations, exceptions)
16.2.5 | Product documentation (extent, format, updates)
16.2.6 | Term and warranties (title, infringement, version, disablement, conformance to documentation, exclusions)
16.2.7 | Software maintenance (term, renewal, services provided, response priorities)
16.2.8 | Indemnity (intellectual property, personal injury, property damage)
16.2.9 | Modifications to product made by client organisation (source code, assignment of rights)
16.2.10 | Disaster recovery (recovery sites, procedures)
16.2.11 | Payment (performance criteria, amounts, timing, audits, expenses policy)
16.2.12 | Confidential information (treatment of confidential information, exclusions)
16.2.13 | Proprietary rights (product ownership, copyright notices)
16.2.14 | Miscellaneous (notices, rights on bankruptcy, relationship of parties, non-exclusivity, successors/assignments, termination, publicity, compliance with regulations)
16.2.15 | Insurance (coverage, terms, responsibility for premiums)
16.2.16 | Termination (supplier default, remedies, survival of provisions)